## ProjectSchedule
Robert Jameson Project Management
Coventry University ¦ 303COM
Final Project | Project Start: | 2017-11-01
| Display Week: | 1 |  |  | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13 | [6 empty] | 2017-11-20 | [6 empty] | 2017-11-27 | [6 empty] | 2017-12-04 | [6 empty] | 2017-12-11 | [6 empty] | 2017-12-18 | [6 empty] | 2017-12-25 | [6 empty] | 2018-01-01 | [6 empty] | 2018-01-08 | [6 empty] | 2018-01-15 | [6 empty] | 2018-01-22 | [6 empty] | 2018-01-29 | [6 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19 | [6 empty] | 2018-02-26 | [6 empty] | 2018-03-05 | [6 empty] | 2018-03-12 | [6 empty] | 2018-03-19 | [6 empty] | 2018-03-26 | [6 empty] | 2018-04-02 | [6 empty] | 2018-04-09 | [6 empty] | 2018-04-16 | [6 empty] | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07
 | time axis 2017-10-30 to 2018-05-13
TASK | PROGRESS | START | END | DAYS | time axis 2017-10-30 to 2018-05-13
Proposal
Initial Blockchain Literature Research | 100% | 2017-11-01 | 2017-11-27 | 27
Initial Blockchain Technologies Research | 100% | 2017-11-27 | 2017-12-05 | 9
Section 1 Proposal Start | 100% | 2017-12-05 | 2018-01-10 | 37
Section 1 Editing | 100% | 2018-01-10 | 2018-01-25 | 16
Section 2 Literature Review Start | 100% | 2018-01-25 | 2018-01-31 | 7
Section 2 Literature Review Improvements | 100% | 2018-01-31 | 2018-02-04 | 5
Reformatting Proposal & Submission | 100% | 2018-02-04 | 2018-02-06 | 3
Proposal Submission | 100% | 2018-02-06 | 2018-02-07 | 2
Development
Start Learning Solidity & Blockchain | 100% | 2018-02-15 | 2018-03-14 | 28
Develop Basic Smart Contract | 100% | 2018-03-14 | 2018-03-22 | 9
Develop NodeJS Server with Basic Frontend | 100% | 2018-03-22 | 2018-04-28 | 38
Add MongoDB & IPFS | 100% | 2018-04-28 | 2018-04-13 | -14
Fix Bugs To Get Application Working | 100% | 2018-04-13 | 2018-04-18 | 6
Add CSS & Finish Development | 100% | 2018-04-18 | 2018-04-19 | 2
Create Video Presentation | 100% | 2018-04-19 | 2018-04-20 | 2
Report Write up
Add Further Dapp examples to Literature Review | 100% | 2018-02-15 | 2018-03-14 | 28
Add Music and ethics section to literature review | 100% | 2018-03-14 | 2018-03-20 | 7
Add IPFS section to Literature review | 100% | 2018-03-25 | 2018-03-28 | 4
Add Blockchain in the future section to literature | 100% | 2018-03-20 | 2018-04-09 | 21
Start Reflection & Ethics | 100% | 2018-03-20 | 2018-04-29 | 41
Remake design and rewrite method | 100% | 2018-03-28 | 2018-04-05 | 9
Edit Questionnaire to better represent website | 100% | 2018-04-09 | 2018-04-13 | 5
Gather Results | 100% | 2018-04-20 | 2018-04-24 | 5
Analyse Results | 100% | 2018-04-24 | 2018-04-26 | 3
Reformatting and Editing | 100% | 2018-04-28 | 2018-04-30 | 3
Submission | 100% | 2018-04-30 | 2018-04-30 | 1
Insert new rows ABOVE this one
Gantt Chart Template: Vertex42 |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.